## Diplomarbeit Juventus HF - Mont
Title | URL | Start date | End date
Terminplanung | https://github.com/Violabitch5/Nathophone_doc/issues/1 | Sep 4, 2025 | Sep 5, 2025
IST-Zustandsanalyse | https://github.com/Violabitch5/Nathophone_doc/issues/4 | Sep 6, 2025 | Sep 7, 2025
Zieldefinition | https://github.com/Violabitch5/Nathophone_doc/issues/3 | Sep 8, 2025 | Sep 9, 2025
Zielgewichtung | https://github.com/Violabitch5/Nathophone_doc/issues/5 | Sep 10, 2025 | Sep 11, 2025
Varianten- & Risikoanalyse | https://github.com/Violabitch5/Nathophone_doc/issues/6 | Sep 12, 2025 | Sep 16, 2025
Variantenauswahl | https://github.com/Violabitch5/Nathophone_doc/issues/7 | Sep 17, 2025 | Sep 17, 2025
Kennzahlberechnung / Limits | https://github.com/Violabitch5/Nathophone_elec/issues/1 | Sep 18, 2025 | Sep 21, 2025
Bauteileevaluation | https://github.com/Violabitch5/Nathophone_elec/issues/2 | Sep 22, 2025 | Sep 30, 2025
Bauteilauswahl | https://github.com/Violabitch5/Nathophone_elec/issues/3 | Oct 1, 2025 | Oct 4, 2025
Print Schema draft | https://github.com/Violabitch5/Nathophone_elec/issues/4 | Oct 5, 2025 | Oct 11, 2025
Print Schema v1 | https://github.com/Violabitch5/Nathophone_elec/issues/5 | Oct 12, 2025 | Oct 18, 2025
Print Layout v1 | https://github.com/Violabitch5/Nathophone_elec/issues/6 | Oct 19, 2025 | Oct 26, 2025
Peer-review Schema und Layout | https://github.com/Violabitch5/Nathophone_elec/issues/7 | Oct 27, 2025 | Oct 31, 2025
Print Schema Final | https://github.com/Violabitch5/Nathophone_elec/issues/8 | Nov 1, 2025 | Nov 3, 2025
Print Layout final | https://github.com/Violabitch5/Nathophone_elec/issues/9 | Nov 3, 2025 | Nov 6, 2025
Gerber-Daten generieren und Printbestellung | https://github.com/Violabitch5/Nathophone_elec/issues/10 | Nov 7, 2025 | Nov 7, 2025
Konstruktion des Korpus fertigstellen | https://github.com/Violabitch5/Nathophone_mech/issues/1 | Nov 8, 2025 | Nov 10, 2025
Herstellung Korpus-Teile | https://github.com/Violabitch5/Nathophone_mech/issues/2 | Nov 11, 2025 | Nov 15, 2025
Zusammenbau Korpus | https://github.com/Violabitch5/Nathophone_mech/issues/3 | Nov 16, 2025 | Nov 22, 2025
BestÃ¼ckung + LÃ¶tarbeit Print | https://github.com/Violabitch5/Nathophone_elec/issues/11 | Nov 23, 2025 | Nov 30, 2025
Funktionstest Print | https://github.com/Violabitch5/Nathophone_elec/issues/12 | Dec 1, 2025 | Dec 4, 2025
Zusammenbau Komplettsystem | https://github.com/Violabitch5/Nathophone_mech/issues/4 | Dec 4, 2025 | Dec 18, 2025
Funktionstests Komplettsystem | https://github.com/Violabitch5/Nathophone_elec/issues/13 | Dec 18, 2025 | Dec 25, 2025
Schlussmessung & Auswertungen | https://github.com/Violabitch5/Nathophone_elec/issues/14 | Dec 25, 2025 | Dec 31, 2025
Audruck (Plakat und Arbeit) | https://github.com/Violabitch5/Nathophone_doc/issues/8 | Jan 1, 2026 | Jan 6, 2026
Abgabe Diplomarbeit | https://github.com/Violabitch5/Nathophone_doc/issues/2 | Jan 7, 2026 | Jan 7, 2026